## Statement
Project Title: | TaskTalk: An Online Educational Collaboration Tool
Project Sponsor: | Rodel N. Villarez
Project Manager: | Madelaine A. Mercado
Jerusa Eden A. Dionco
Adrian Ace D. Carbon
Jose Enrico P. Leuterio
Jefferson Matthew Y. Uy
Project Statement: | The group will develop a web-based collaboration tool called TaskTalk that is responsible for keeping track of academic group projects. It will eliminate the use of personal accounts in school works and provide an environment where students and professors can collaborate and organize projects by assigning project roles to each group members, track deadlines, monitor progress and upload project files. This will result to an easier collaboration and task management to the academic industry. The project will be completed on February 20, 2022.
Created on: | September 5, 2021
Last updated on: | November 29, 2021
Project Statement
Note on B3: ====== ID#AAAARPUzxqY Author (2021-10-25 05:18:14) Please enter project information below. Information entered here will automatically update all the worksheets in this file.
Note on B9: ====== ID#AAAARPRRgYw Author (2021-10-25 05:18:14) Project Statement Include an action and an end result (performance), a target completion date (time), and an overall project budget (cost).

## Objectives
Last updated on: The group will develop a web-based collaboration tool called TaskTalk that is responsible for keeping track of academic group projects. It will eliminate the use of personal accounts in school works and provide an environment where students and professors can collaborate and organize projects by assigning project roles to each group members, track deadlines, monitor progress and upload project files. This will result to an easier collaboration and task management to the academic industry. The project will be completed on February 20, 2022.
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
Develop Objectives | Identify Measures | Set Standards
Communication & Immersion | Develop a communication tool for | The system should have enough
| synchronous and asynchronous | tools to make communication
| communication. To share files with | easier.
ease and orderly.
Add a real-time chatting system
To enable students keep in touch
with their classmates, to keep a
classroom like environment.
Interact with teams from different
locations.
To enable students keep in touch
with their classmates, to keep a
classroom like environment.
Organization | Organize and properly manage | Tools to organize works easily.
projects using only one app.
Create, assign, and manage tasks.
Create a proper project plan to
complete it on time.
Provide Transparency to team
members about tasks and the
overall project progress.
Create a proper project plan to
complete it on time.
One Platform | Give students a platform wherein
they can provide updates with their
given tasks.
Note on C9: ====== ID#AAAARPRRgYM Author (2021-10-25 05:18:14) Develop Objectives What value should this project produce? What short- and long-term benefits do we want? What constraints, restrictions, or resource limitations do we face? What requirements must be met?
Note on E9: ====== ID#AAAARPUzxqo Author (2021-10-25 05:18:14) Identify Measures How will the objectives be measured?
Note on G9: ====== ID#AAAARPRRgY0 Author (2021-10-25 05:18:14) Set Standards What is the minimum and/or target level of performance?
Project Objectives

## Project Limitation
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
Limitations | Description
The system is designed for students and teachers.
Limited to the teachers and students of PUP.
It is a tool used for Collaborating to teachers and with your classmates.
Limitation
The system is for Teacher to student platform.
The system is limited to PUP students.
It is an Online Collaboration tool not an LMS.

## WBS_RR
Last updated on: The group will develop a web-based collaboration tool called TaskTalk that is responsible for keeping track of academic group projects. It will eliminate the use of personal accounts in school works and provide an environment where students and professors can collaborate and organize projects by assigning project roles to each group members, track deadlines, monitor progress and upload project files. This will result to an easier collaboration and task management to the academic industry. The project will be completed on February 20, 2022.
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
|  | Knowledge/Skills |  |  |  | Facilities |  |  |  | Equipment |  |  |  | Materials |  |  |  | Special Resources
WBS Code* | Develop Work Breakdown Structure | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Type | Amt | Unit Cost | Total Cost | Total
1 | Project Planning |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.1 | Research about similar systems |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.2 | Research about features from similar systems |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.3 | Learn about Monday.com |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.4 | Learn XAMPP |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.5 | Learn PHP |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.6 | Learn HTML |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.7 | Learn CSS |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.8 | Learn MySql |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.9 | Learn Javascript |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.1 | Study Front-end |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
1.11 | Study Back-end |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
2 | ERD and Flowchart |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
2.1 | Designing of Database Schema |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
2.2 | Design a System Wireframe |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
2.3 | Plan the system flow using flowchart |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3 | Theme of the system(GUI) |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.1 | Design Index UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.2 | Design Sign-up UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.3 | Design Login UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.4 | Design Dashboard UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.5 | Design Project List UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.6 | Design Project Board UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.7 | Design Taskboard UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.8 | Design Collaboration Board UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.9 | Design Grading Sheet UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.1 | Design Messaging UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.11 | Design Calendar UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.12 | Design User Profile UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
3.13 | Design System Admin UI |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4 | Development of the Project |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.1 | Set up of front-end and back-end |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.2 | Dashboard |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.3 | Sign up and Sign in Modules |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.4 | Chat Module |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.5 | Calendar Module |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.6 | Notification Module |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.7 | Teacher and Student Modules |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.7.1 | Announcement Module |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.7.2 | Task Module |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.7.3 | File-upload Module |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.8 | Forms |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.8.1 | Project Creation Form |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.8.2 | Group Creation Form |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.8.3 | Task Creation Form |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.8.4 | Subtask Creation Form |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.9 | Create Database |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.9.1 | Connection of Database |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
4.9.2 | Identify the data needed |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
5 | Project Execution |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
5.1 | Unit and Integration Testing |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
5.2 | System and Acceptance Testing |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
5.3 | Software Testing |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
5.4 | Debugging |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
6 | Deployment |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
6.1 | Study about Web Hosting |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
6.2 | Buy domain name and database hosting |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
[5 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 | 0
Note on H8: ====== ID#AAAARPUzxqk Author (2021-10-25 05:18:14) Identify Resource Requirements What knowledge and skills are needed?
Note on M8: ====== ID#AAAARPUzxqc Author (2021-10-25 05:18:14) Identify Resource Requirements What facilities are needed?
Note on R8: ====== ID#AAAARPRRgYs Author (2021-10-25 05:18:14) Identify Resource Requirements What equipment is needed?
Note on W8: ====== ID#AAAARPUzxqg Author (2021-10-25 05:18:14) Identify Resource Requirements What materials are needed?
Note on AB8: ====== ID#AAAARPUzxqs Author (2021-10-25 05:18:14) Identify Resource Requirements What special resources are needed?
Note on E9: ====== ID#AAAARPUzxqU Author (2021-10-25 05:18:14) Develop Work Breakdown Structure • What are the major outputs of this project? • What are the components of each output? • What work needs to be done to achieve the objectives? • How should work be organized to ease planning and control?
Work Breakdown Structure
Resource Requirements
Responsibility Assignment Matrix

## RAM
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado |  | Assign Responsibility
Project Statement: Adrian Ace D. Carbon
People/Departments
WBS Code | Develop Work Breakdown Structure | Back-End | Q.A/ Back-End | Front-End | Q.A/ Front-End | Researcher/Database Admin
1 | Project Planning
1.1 | Research about similar systems |  |  |  |  | Ace Carbon
1.2 | Research about features from similar systems |  |  |  |  | Ace Carbon
1.3 | Learn about Monday.com |  |  |  |  | Ace Carbon
1.4 | Learn XAMPP | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
1.5 | Learn PHP | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
1.6 | Learn HTML | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
1.7 | Learn CSS | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
1.8 | Learn MySql | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
1.9 | Learn Javascript | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
1.1 | Study Front-end |  |  | Jefferson Uy | Jose Leuterio
1.11 | Study Back-end | Madelaine Mercado | Jerusa Dionco
2 | ERD and Flowchart
2.1 | Designing of Database Schema | Madelaine Mercado | Jerusa Dionco |  |  | Ace Carbon
2.2 | Design a System Wireframe |  |  | Jefferson Uy | Jose Leuterio
2.3 | Plan the system flow using flowchart |  | Jerusa Dionco |  |  | Ace Carbon
3 | Theme of the system(GUI)
3.1 | Design Index UI |  |  | Jefferson Uy | Jose Leuterio
3.2 | Design Sign-up UI |  | Jerusa Dionco
3.3 | Design Login UI |  | Jerusa Dionco
3.4 | Design Dashboard UI | Madelaine Mercado |  | Jefferson Uy
3.5 | Design Project List UI | Madelaine Mercado |  | Jefferson Uy
3.6 | Design Project Board UI | Madelaine Mercado |  | Jefferson Uy
3.7 | Design Taskboard UI | Madelaine Mercado |  | Jefferson Uy
3.8 | Design Collaboration Board UI |  | Jerusa Dionco
3.9 | Design Grading Sheet UI | Madelaine Mercado
3.1 | Design Messaging UI |  |  |  | Jose Leuterio
3.11 | Design Calendar UI |  |  |  | Jose Leuterio
3.12 | Design User Profile UI | Madelaine Mercado |  | Jefferson Uy
3.13 | Design System Admin UI |  |  |  |  | Ace Carbon
4 | Development of the Project
4.1 | Set up of front-end and back-end | Madelaine Mercado | Jerusa Dionco | Jefferson Uy
4.2 | Dashboard | Madelaine Mercado
4.3 | Sign up and Sign in Modules |  | Jerusa Dionco
4.4 | Chat Module | Madelaine Mercado
4.5 | Calendar Module |  |  |  | Jose Leuterio
4.6 | Notification Module | Madelaine Mercado
4.7 | Teacher and Student Modules
4.7.1 | Announcement Module | Madelaine Mercado
4.7.2 | Task Module | Madelaine Mercado
4.7.3 | File-upload Module |  | Jerusa Dionco
4.8 | Forms
4.8.1 | Project Creation Form | Madelaine Mercado
4.8.2 | Group Creation Form | Madelaine Mercado
4.8.3 | Task Creation Form | Madelaine Mercado
4.8.4 | Subtask Creation Form |  | Jerusa Dionco
4.9 | Create Database
4.9.1 | Connection of Database | Madelaine Mercado | Jerusa Dionco
4.9.2 | Identify the data needed |  |  | Jefferson Uy | Jose Leuterio | Ace Carbon
5 | Project Execution
5.1 | Unit and Integration Testing |  |  | Jefferson Uy | Jose Leuterio | Ace Carbon
5.2 | System and Acceptance Testing |  |  | Jefferson Uy | Jose Leuterio | Ace Carbon
5.3 | Software Testing |  |  | Jefferson Uy | Jose Leuterio | Ace Carbon
5.4 | Debugging | Madelaine Mercado | Jerusa Dionco
6 | Deployment
6.1 | Study about Web Hosting | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
6.2 | Buy domain name and database hosting | Madelaine Mercado | Jerusa Dionco | Jefferson Uy | Jose Leuterio | Ace Carbon
Work Breakdown Structure
Resource Requirements
Responsibility Assignment Matrix
Note on I6: ====== ID#AAAARPRRgY4 Author (2021-10-25 05:18:14) What resources (people/department/etc.) are responsible for completing each WBS task?
Note on E9: ====== ID#AAAARPRRgYo Author (2021-10-25 05:18:14) Develop Work Breakdown Structure • What are the major outputs of this project? • What are the components of each output? • What work needs to be done to achieve the objectives? • How should work be organized to ease planning and control?

## CPM
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado |  | Critical Path Method (CPM) |  |  | Sequence Deliverables (in days) |  |  |  |  | Schedule Deliverables (in calendar time)
Project Statement: Adrian Ace D. Carbon
|  |  |  | Critical | Earliest |  | Latest |  |  | Planned |  | Actual
WBS Code | Develop Work Breakdown Structure | Precedence | Duration | Path? | Start | Finish* | Start** | Finish | Slack*** | Start | Finish | Start | Finish | Notes
1 | Project Planning |  | 98 |  |  | 98 | -98 |  | -98
1.1 | Research about similar systems |  | 7 |  |  | 7 | -7 |  | -7
1.2 | Research about features from similar systems |  | 7 |  |  | 7 | -7 |  | -7
1.3 | Learn about Monday.com |  | 5 |  |  | 5 | -5 |  | -5
1.4 | Learn XAMPP |  | 10 |  |  | 10 | -10 |  | -10
1.5 | Learn PHP |  | 7 |  |  | 7 | -7 |  | -7
1.6 | Learn HTML |  | 14 |  |  | 14 | -14 |  | -14
1.7 | Learn CSS |  | 14 |  |  | 14 | -14 |  | -14
1.8 | Learn MySql |  | 7 |  |  | 7 | -7 |  | -7
1.9 | Learn Javascript |  | 7 |  |  | 7 | -7 |  | -7
1.1 | Study Front-end |  | 20 |  |  | 20 | -20 |  | -20
1.11 | Study Back-end |  | 20 |  |  | 20 | -20 |  | -20
2 | ERD and Flowchart |  | 19 |  |  | 19 | -19 |  | -19
2.1 | Designing of Database Schema |  | 2 |  |  | 2 | -2 |  | -2
2.2 | Design a System Wireframe |  | 15 |  |  | 15 | -15 |  | -15
2.3 | Plan the system flow using flowchart |  | 2 |  |  | 2 | -2 |  | -2
3 | Theme of the system(GUI) |  | 38 |  |  | 38 | -38 |  | -38
3.1 | Design Index UI |  | 3 |  |  | 3 | -3 |  | -3
3.2 | Design Sign-up UI |  | 2 |  |  | 2 | -2 |  | -2
3.3 | Design Login UI |  | 2 |  |  | 2 | -2 |  | -2
3.4 | Design Dashboard UI |  | 5 |  |  | 5 | -5 |  | -5
3.5 | Design Project List UI |  | 4 |  |  | 4 | -4 |  | -4
3.6 | Design Project Board UI |  | 4 |  |  | 4 | -4 |  | -4
3.7 | Design Taskboard UI |  | 4 |  |  | 4 | -4 |  | -4
3.8 | Design Collaboration Board UI |  | 3 |  |  | 3 | -3 |  | -3
3.9 | Design Grading Sheet UI |  | 1 |  |  | 1 | -1 |  | -1
3.1 | Design Messaging UI |  | 2 |  |  | 2 | -2 |  | -2
3.11 | Design Calendar UI |  | 2 |  |  | 2 | -2 |  | -2
3.12 | Design User Profile UI |  | 3 |  |  | 3 | -3 |  | -3
3.13 | Design System Admin UI |  | 3 |  |  | 3 | -3 |  | -3
4 | Development of the Project |  | 266 |  |  | 266 | -266 |  | -266
4.1 | Set up of front-end and back-end |  | 60 |  |  | 60 | -60 |  | -60
4.2 | Dashboard |  | 20 |  |  | 20 | -20 |  | -20
4.3 | Sign up and Sign in Modules |  | 10 |  |  | 10 | -10 |  | -10
4.4 | Chat Module |  | 10 |  |  | 10 | -10 |  | -10
4.5 | Calendar Module |  | 3 |  |  | 3 | -3 |  | -3
4.6 | Notification Module |  | 7 |  |  | 7 | -7 |  | -7
4.7 | Teacher and Student Modules |  |  |  |  | 0 | 0 |  | 0
4.7.1 | Announcement Module |  | 10 |  |  | 10 | -10 |  | -10
4.7.2 | Task Module |  | 30 |  |  | 30 | -30 |  | -30
4.7.3 | File-upload Module |  | 11 |  |  | 11 | -11 |  | -11
4.8 | Forms |  |  |  |  | 0 | 0 |  | 0
4.8.1 | Project Creation Form |  | 60 |  |  | 60 | -60 |  | -60
4.8.2 | Group Creation Form |  | 10 |  |  | 10 | -10 |  | -10
4.8.3 | Task Creation Form |  | 10 |  |  | 10 | -10 |  | -10
4.8.4 | Subtask Creation Form |  | 10 |  |  | 10 | -10 |  | -10
4.9 | Create Database |  |  |  |  | 0 | 0 |  | 0
4.9.1 | Connection of Database |  | 12 |  |  | 12 | -12 |  | -12
4.9.2 | Identify the data needed |  | 3 |  |  | 3 | -3 |  | -3
5 | Project Execution |  | 16 |  |  | 16 | -16 |  | -16
5.1 | Unit and Integration Testing |  | 3 |  |  | 3 | -3 |  | -3
5.2 | System and Acceptance Testing |  | 3 |  |  | 3 | -3 |  | -3
5.3 | Software Testing |  | 3 |  |  | 3 | -3 |  | -3
5.4 | Debugging |  | 7 |  |  | 7 | -7 |  | -7
6 | Deployment |  | 10 |  |  | 10 | -10 |  | -10
6.1 | Study about Web Hosting |  | 5 |  |  | 5 | -5 |  | -5
6.2 | Buy domain name and database hosting |  | 5 |  |  | 5 | -5 |  | -5
[6 empty] | 0 | 0 |  | 0
|  | * Earliest Finish = Earliest Start + Duration |  |  |  | *** Slack = Latest Finish – Earliest Finish
** Latest Start = Latest finish – Duration
Note on P6: ====== ID#AAAARPRRgYU Author (2021-10-25 05:18:14) Sequence Deliverables • In what order must work packages be completed? • What knowledge, experience, templates, or historical information exists? • How much elapsed time will each work package take given the type and availability of resources?
Note on Y6: ====== ID#AAAARPRRgYc Author (2021-10-25 05:18:14) Schedule Deliverables • What assumptions are being made about working time, resource availability, or other constraints? • When should work packages start and finish in calendar time?
Note on E9: ====== ID#AAAARPRRgZA Author (2021-10-25 05:18:14) Develop Work Breakdown Structure • What are the major outputs of this project? • What are the components of each output? • What work needs to be done to achieve the objectives? • How should work be organized to ease planning and control?
Work Breakdown Structure
Resource Requirements
Sequence and Schedule Deliverables

## Gantt
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
|  |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
WBS Code | Develop Work Breakdown Structure | Precedence | Duration | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Project Planning | 0 | 98
1.1 | Research about similar systems | 0 | 7
1.2 | Research about features from similar systems | 0 | 7
1.3 | Learn about Monday.com | 0 | 5
1.4 | Learn XAMPP | 0 | 10
1.5 | Learn PHP | 0 | 7
1.6 | Learn HTML | 0 | 14
1.7 | Learn CSS | 0 | 14
1.8 | Learn MySql | 0 | 7
1.9 | Learn Javascript | 0 | 7
1.1 | Study Front-end | 0 | 20
1.11 | Study Back-end | 0 | 20
2 | ERD and Flowchart | 0 | 19
2.1 | Designing of Database Schema | 0 | 2
2.2 | Design a System Wireframe | 0 | 15
2.3 | Plan the system flow using flowchart | 0 | 2
3 | Theme of the system(GUI) | 0 | 38
3.1 | Design Index UI | 0 | 3
3.2 | Design Sign-up UI | 0 | 2
3.3 | Design Login UI | 0 | 2
3.4 | Design Dashboard UI | 0 | 5
3.5 | Design Project List UI | 0 | 4
3.6 | Design Project Board UI | 0 | 4
3.7 | Design Taskboard UI | 0 | 4
3.8 | Design Collaboration Board UI | 0 | 3
3.9 | Design Grading Sheet UI | 0 | 1
3.1 | Design Messaging UI | 0 | 2
3.11 | Design Calendar UI | 0 | 2
3.12 | Design User Profile UI | 0 | 3
3.13 | Design System Admin UI | 0 | 3
4 | Development of the Project | 0 | 266
4.1 | Set up of front-end and back-end | 0 | 60
4.2 | Dashboard | 0 | 20
4.3 | Sign up and Sign in Modules | 0 | 10
4.4 | Chat Module | 0 | 10
4.5 | Calendar Module | 0 | 3
4.6 | Notification Module | 0 | 7
4.7 | Teacher and Student Modules | 0 | 0
4.7.1 | Announcement Module | 0 | 10
4.7.2 | Task Module | 0 | 30
4.7.3 | File-upload Module | 0 | 11
4.8 | Forms | 0 | 0
4.8.1 | Project Creation Form | 0 | 60
4.8.2 | Group Creation Form | 0 | 10
4.8.3 | Task Creation Form | 0 | 10
4.8.4 | Subtask Creation Form | 0 | 10
4.9 | Create Database | 0 | 0
4.9.1 | Connection of Database | 0 | 12
4.9.2 | Identify the data needed | 0 | 3
5 | Project Execution | 0 | 16
5.1 | Unit and Integration Testing | 0 | 3
5.2 | System and Acceptance Testing | 0 | 3
5.3 | Software Testing | 0 | 3
5.4 | Debugging | 0 | 7
6 | Deployment | 0 | 10
6.1 | Study about Web Hosting | 0 | 5
6.2 | Buy domain name and database hosting | 0 | 5
Note on E9: ====== ID#AAAARPRRgY8 Author (2021-10-25 05:18:14) Develop Work Breakdown Structure • What are the major outputs of this project? • What are the components of each output? • What work needs to be done to achieve the objectives? • How should work be organized to ease planning and control?
Work Breakdown Structure
Resource Requirements
Gantt

## PPA
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool |  | Protect the Plan
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
WBS Code | Develop Work Breakdown Structure | List Potential Problems | P* | S** | Identify Likely Causes | Take Preventive Action | Plan Contingent Action | Identify Triggers | Steps/Modifications to the Plan | Who | When
1 | Project Planning
1.1 | Research about similar systems
1.2 | Research about features from similar systems
1.3 | Learn about Monday.com
1.4 | Learn XAMPP
1.5 | Learn PHP
1.6 | Learn HTML
1.7 | Learn CSS
1.8 | Learn MySql
1.9 | Learn Javascript
1.1 | Study Front-end
1.11 | Study Back-end
2 | ERD and Flowchart
2.1 | Designing of Database Schema
2.2 | Design a System Wireframe
2.3 | Plan the system flow using flowchart
3 | Theme of the system(GUI)
3.1 | Design Index UI
3.2 | Design Sign-up UI
3.3 | Design Login UI
3.4 | Design Dashboard UI
3.5 | Design Project List UI
3.6 | Design Project Board UI
3.7 | Design Taskboard UI
3.8 | Design Collaboration Board UI
3.9 | Design Grading Sheet UI
3.1 | Design Messaging UI
3.11 | Design Calendar UI
3.12 | Design User Profile UI
3.13 | Design System Admin UI
4 | Development of the Project
4.1 | Set up of front-end and back-end
4.2 | Dashboard
4.3 | Sign up and Sign in Modules
4.4 | Chat Module
4.5 | Calendar Module
4.6 | Notification Module
4.7 | Teacher and Student Modules
4.7.1 | Announcement Module
4.7.2 | Task Module
4.7.3 | File-upload Module
4.8 | Forms
4.8.1 | Project Creation Form
4.8.2 | Group Creation Form
4.8.3 | Task Creation Form
4.8.4 | Subtask Creation Form
4.9 | Create Database
4.9.1 | Connection of Database
4.9.2 | Identify the data needed
5 | Project Execution
5.1 | Unit and Integration Testing
5.2 | System and Acceptance Testing
5.3 | Software Testing
5.4 | Debugging
6 | Deployment
6.1 | Study about Web Hosting
6.2 | Buy domain name and database hosting
*P = Probability **S = Seriousness
Work Breakdown Structure
Resource Requirements
Potential Problem Analysis (PPA)
z
Note on H5: ====== ID#AAAARPRRgYk Author (2021-10-25 05:18:14) Protect the Plan • Where is time, cost, and performance most at risk? • What could go wrong? • What is the likelihood of this potential problem occurring? • What will be the impact? • What could cause this potential problem? • How can we prevent this likely cause? • What will we do if this happens? • How will we know it has occurred?
Note on E9: ====== ID#AAAARPRRgYg Author (2021-10-25 05:18:14) Develop Work Breakdown Structure • What are the major outputs of this project? • What are the components of each output? • What work needs to be done to achieve the objectives? • How should work be organized to ease planning and control?

## POA (hidden)
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool |  | Enhance the Plan
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
WBS Code | Develop Work Breakdown Structure | List Potential Opportunities | P* | B** | Identify Likely Causes | Take Promoting Action | Plan Capitalizing Action | Identify Triggers | Steps/Modifications to the Plan | Who | When
1 | Project Planning
1.1 | Research about similar systems
1.2 | Research about features from similar systems
1.3 | Learn about Monday.com
1.4 | Learn XAMPP
1.5 | Learn PHP
1.6 | Learn HTML
1.7 | Learn CSS
1.8 | Learn MySql
1.9 | Learn Javascript
1.1 | Study Front-end
1.11 | Study Back-end
2 | ERD and Flowchart
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
#REF! | #REF!
*P = Probability **B = Benefit
Note on H5: ====== ID#AAAARPRRgYQ Author (2021-10-25 05:18:14) Enhance the Plan • Where are there significant opportunities? • What could go better than expected? • What is the likelihood of this potential opportunity occurring? • What will be the benefit? • What could cause this potential opportunity? • How can we promote this likely cause? • What will we do if this happens? • How will we know if it has occurred?
Note on E9: ====== ID#AAAARPRRgYY Author (2021-10-25 05:18:14) Develop Work Breakdown Structure • What are the major outputs of this project? • What are the components of each output? • What work needs to be done to achieve the objectives? • How should work be organized to ease planning and control?
Resource Requirements
Potential Opportunity Analysis (POA)
Work Breakdown Structure
z

## Implement
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
Start to Implement Checklist
What type of formal project kickoff meeting is required?
What other communication about the initiation of work might be required or useful?
What documentation might be useful or necessary during any kickoff communications?
What ground rules will be necessary for the entire team, or subgroups of the team, to operate efficiently?
Are specific policies or protocols for changes required?
What type of virtual or office space is required?
What else?
Start to Implement
Individual and/or group communications planned
Project documentation assembled to guide implementation
Materials, facilities, equipment, funding, etc., in place for initial tasks
Ground rules established for team interaction, communication
Potential Problem/Opportunity Analysis done for critical initial tasks
Team and team member performance systems agreed to and in place
Monitoring systems and methods agreed to
and in place
Issue resolution protocols agreed to and in place
Reporting systems and methods agreed to
and in place
Change control systems agreed to and in place

## Change Auth.
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
Change Description:
Change Impact:
Change Alternatives Considered:
Anticipated Problems, Implications, Resolution:
Change Authorization
Change Authorization Number:
Submitted by: Date:
Authorized by: Date:

## Closeout
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
Closeout and Evaluate Checklist | Summarize the Project
Did the project satisfy the project statement? If not, explain why.
How well were project objectives satisfied? How well were customers, sponsors, and end users satisfied with the project? If any objectives were not met, explain why.
How well did the project stay on schedule? If any major deliverables were early or late, explain why. How well did the team adjust to schedule changes?
How well were resources estimated overall? How did actual use of resources compare to the plan? How did changes in resource availability affect overall implementation?
How well did the team work together? How were performance expectations set and maintained?
How well were performance expectations satisfied during the project?
What, if any, changes were made to project definition after implementation started? Why?
What, if any, changes were made to the project plan after implementation started? Why?
How will you improve the next project you do?
Closeout and Evaluate
Deliverables all completed
Contingent actions disabled
Capitalizing actions disabled
Project accounts closed
Team members recognized
Owners, sponsors, vendors notified of close
Results documented
Documents archived

## Appendix
Last updated on: manually enter date updated
Project Title: TaskTalk: An Online Educational Collaboration Tool
Project Manager: Madelaine A. Mercado
Project Statement: Adrian Ace D. Carbon
Meeting No | Location and Summary
Minutes of the Meeting
Minutes 1
Minutes 2
Minutes 3
Minutes 4